## ProjectSchedule
|  |  |  | Project Start: |  | 2023-07-01
|  |  |  | Display Week: |  | 5 |  |  | 2023-07-24 | [6 empty] | 2023-07-31 | [6 empty] | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25 | [6 empty] | 2023-10-02 | [6 empty] | 2023-10-09 | [6 empty] | 2023-10-16 | [6 empty] | 2023-10-23 | [6 empty] | 2023-10-30 | [6 empty] | 2023-11-06 | [6 empty] | 2023-11-13 | [6 empty] | 2023-11-20 | [6 empty] | 2023-11-27 | [6 empty] | 2023-12-04 | [6 empty] | 2023-12-11 | [6 empty] | 2023-12-18 | [6 empty] | 2023-12-25 | [6 empty] | 2024-01-01 | [6 empty] | 2024-01-08 | [6 empty] | 2024-01-15 | [6 empty] | 2024-01-22 | [6 empty] | 2024-01-29 | [6 empty] | 2024-02-05 | [6 empty] | 2024-02-12
 | time axis 2023-07-24 to 2024-02-18
Section | System | Phase | Part | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2023-07-24 to 2024-02-18
|  | Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule. |  |  |  | -7
Suspension | Upright | Design | Front Upright | Joseph | 100% | 2023-06-12 | 2023-06-19 | 8
Suspension | Upright | Design | Rear Upright | Joseph | 100% | 2023-06-17 | 2023-06-24 | 8
Suspension | Upright | Design | Camber Adjustment | Joseph | 100% | 2023-06-17 | 2023-06-24 | 8
Suspension | Spindles | Design | Front Spindle | Joseph | 100% | 2023-06-17 | 2023-06-24 | 8
Suspension | Spindles | Design | Rear Spindle | Joseph | 100% | 2023-06-17 | 2023-06-24 | 8
Suspension | Bellcrank | Design | Front Bellcrank | Joseph | 100% | 2023-07-01 | 2023-07-08 | 8
Suspension | Bellcrank | Design | Rear Bellcrank | Joseph | 100% | 2023-07-01 | 2023-07-08 | 8
Suspension | Wheel attach | Design | Wheel Lugs | Hunter | 100% | 2023-07-08 | 2023-07-15 | 8
Suspension | Control Arm | Design | Control Arm | Caleb | 100% | 2023-07-15 | 2023-07-22 | 8
Suspension | Rods | Design | Steering | Caleb | 100% | 2023-07-22 | 2023-07-29
Suspension | Rods | Design | Toe | Caleb | 100% | 2023-07-22 | 2023-07-29
Suspension | Wheel attach | Design | Wheel nuts | Caleb | 100% | 2023-07-22 | 2023-07-29
Suspension | Anti Roll bar | Design | Anti Roll bar | Hunter | 100% | 2023-07-22 | 2023-07-29
Chassis | Chassis | Design | Chassis | Roxanne | 76% | 2023-07-24 | 2023-07-31 | 8
Suspension | Rods | Design | Front Push | Caleb | 100% | 2023-07-29 | 2023-08-05 | 8
Suspension | Rods | Design | Rear Push | Caleb | 100% | 2023-07-29 | 2023-08-05 | 8
Powertrain | Exhaust | Design | 1/4 Wave Resonator | Austin | 50% | 2023-07-29 | 2023-08-05 | 8
Chassis | Front | Design | Anti Intrusion Plate | Roxanne | 76% | 2023-07-29 | 2023-08-05 | 8
Powertrain | Intake | Design | Throttle Body | Jacob | 95% | 2023-08-05 | 2023-08-12 | 8
Drivetrain | Brakes | Design | Calculations | Hayden/Brennan | 100% | 2023-08-05 | 2023-08-12 | 8
Drivetrain | Power Transfer | Design | Sprocket | Joey | 95% | 2023-08-05 | 2023-08-12 | 8
Drivetrain | Power Transfer | Design | Tripod bearing housing | Joey | 90% | 2023-08-05 | 2023-08-12 | 8
Drivetrain | Power Transfer | Design | Tripod bearings | Joey | 90% | 2023-08-05 | 2023-08-12 | 8
Controls | Steering | Design | Wheel | Nathan | 90% | 2023-08-05 | 2023-08-12 | 8
Controls | Shifting | Design | Paddles | Nathan | 90% | 2023-08-05 | 2023-08-12 | 8
Controls | Shifting | Design | Motor | Nathan | 90% | 2023-08-05 | 2023-08-12 | 8
Controls | Shifting | Design | Wiring | Nathan | 70% | 2023-08-05 | 2023-08-12 | 8
Aerodynamics | Bodywork | Design | Bodywork | Owen | 75% | 2023-08-09 | 2023-08-16 | 8
Business | Recruitment | Business | Reserve Conference Room |  | 100% | 2023-08-09 | 2023-08-16 | 8
Drivetrain | Brakes | Design | Buttons drawing | Hayden/Brennan | 100% | 2023-08-12 | 2023-08-19 | 8
Electrical | Harness | Design | Battery |  | 100% | 2023-08-12 | 2023-08-19 | 8
Electrical | Harness | Design | Harness |  | 50% | 2023-08-19 | 2023-08-26 | 8
Aerodynamics | Bodywork | Design | Mounting | Owen | 0% | 2023-08-12 | 2023-08-19 | 8
Controls | Floorplate | Design | Floorplate | Owen | 100% | 2023-08-12 | 2023-08-19 | 8
Controls | Floorplate | Design | Mold | Owen | 0% | 2023-08-12 | 2023-08-19 | 8
Controls | Floorplate | Design | Mounting | Owen | 100% | 2023-08-12 | 2023-08-19 | 8
Aerodynamics | Bodywork | Design | Mold | Owen | 10% | 2023-08-13 | 2023-08-20 | 8
Powertrain | Cooling | Design | Cooling Fill Cap | Jacob | 90% | 2023-08-19 | 2023-08-26 | 8
Powertrain | Exhaust | Design | Muffler | Austin | 80% | 2023-08-19 | 2023-08-26 | 8
Powertrain | Cooling | Design | Radiators | Hayden | 85% | 2023-08-19 | 2023-08-26 | 8
Drivetrain | Power Transfer | Design | Sprocket Mount | Joey | 10% | 2023-08-19 | 2023-08-26 | 8
Electrical | Harness | Design | Wire Mangement |  | 100% | 2023-08-19 | 2023-08-26 | 8
Electrical | Harness | Design | Rectifier |  | 90% | 2023-08-26 | 2023-09-02 | 8
Controls | Shifting | Design | Controller Mounting | Nathan | 0% | 2023-08-19 | 2023-08-26 | 8
Aerodynamics | Top Plate | Design | Top Plate | Owen | 75% | 2023-08-19 | 2023-08-26 | 8
Controls | Shifting | Design | Motor Mount | Nathan | 90% | 2023-08-19 | 2023-08-26 | 8
Drivetrain | Brakes | Design | Cylinder Geometry | Hayden/Brennan | 0% | 2023-08-19 | 2023-08-26 | 8
Drivetrain | Brakes | Design | Front System Routing | Hayden/Brennan | 0% | 2023-08-19 | 2023-08-26 | 8
Drivetrain | Brakes | Design | Rear System Routing | Hayden/Brennan | 0% | 2023-08-19 | 2023-08-26 | 8
Chassis | Chassis | Design | Paper Profile | Roxanne | 95% | 2023-08-19 | 2023-08-26 | 8
Chassis | Jig | Design | Wood |  | 0% | 2023-08-19 | 2023-08-26 | 8
Controls | Steering | Design | Column | Colin | 100% | 2023-08-19 | 2023-08-26 | 8
Controls | Steering | Design | Column Mount | Colin | 80% | 2023-08-19 | 2023-08-26 | 8
Controls | Steering | Design | Rack Mount | Colin | 0% | 2023-08-19 | 2023-08-26 | 8
Business | PR | Business | August Newsletter |  | 100% | 2023-08-19 | 2023-08-26 | 8
Chassis | Chassis | Manufacture | Paper Profile |  | 0% | 2023-08-23 | 2023-08-30 | 8
Powertrain | Cooling | Design | Mounting | Jacob | 0% | 2023-08-26 | 2023-09-02 | 8
Powertrain | Exhaust | Design | Helmholtz Resonator | Austin | 50% | 2023-08-26 | 2023-09-02 | 8
Electrical | Mounting | Design | Fueltech |  | 90% | 2023-08-26 | 2023-09-02 | 8
Electrical | Mounting | Design | Starter solenoid |  | 90% | 2023-08-26 | 2023-09-02 | 8
Aerodynamics | Top Plate | Design | Mounting | Owen | 0% | 2023-08-26 | 2023-09-02 | 8
Drivetrain | Chassis Mounting | Design | Tensioner | Jackson | 0% | 2023-08-26 | 2023-09-02 | 8
Drivetrain | Chassis Mounting | Design | Diff Plates | Jackson | 0% | 2023-08-26 | 2023-09-02 | 8
Drivetrain | Chassis Mounting | Design | Jig | Jackson | 0% | 2023-08-26 | 2023-09-02 | 8
Chassis | Jig | Design | Jig |  | 0% | 2023-08-26 | 2023-09-02 | 8
Chassis | Jig | Design | 3d Print |  | 0% | 2023-08-26 | 2023-09-02 | 8
Controls | Shifting | Design | Code | Nathan | 0% | 2023-08-26 | 2023-09-02 | 8
Business | Recruitment | Business | Recruitment Meeting |  | 100% | 2023-09-01 | 2023-09-08 | 8
Powertrain | Exhaust | Design | Tubing | Hayden | 0% | 2023-09-02 | 2023-09-09 | 8
Powertrain | Fuel | Design | Filler Neck | Jacob/Will | 0% | 2023-09-02 | 2023-09-09 | 8
Controls | Firewall | Design | Firewall | Owen | 20% | 2023-09-02 | 2023-09-09 | 8
Controls | Firewall | Design | Mounting | Owen | 0% | 2023-09-02 | 2023-09-09 | 8
Controls | Firewall | Design | Mold | Owen | 0% | 2023-09-02 | 2023-09-09 | 8
Controls | Pedal Tray | Design | Pedal Tray | Colin/Kensly | 10% | 2023-09-02 | 2023-09-09 | 8
Controls | Clutch | Design | Clutch | Colin/Kensly | 0% | 2023-09-02 | 2023-09-09 | 8
Electrical | Mounting | Design | coil |  | 90% | 2023-09-02 | 2023-09-09 | 8
Electrical | Mounting | Design | AFR Gauge |  | 90% | 2023-09-02 | 2023-09-09 | 8
Powertrain | Intake | Design | Runner | Jacob | 0% | 2023-09-09 | 2023-09-16 | 8
Powertrain | Cooling | Design | Aluminium Tubing | Jacob | 100% | 2023-09-09 | 2023-09-16 | 8
Powertrain | Cooling | Design | Hoses | Jacob | 100% | 2023-09-09 | 2023-09-16 | 8
Chassis | Chassis | Manufacture | Cut Tubes |  | 0% | 2023-09-09 | 2023-09-16 | 8
Chassis | Chassis | Manufacture | Prep Tubes |  | 0% | 2023-09-09 | 2023-09-16 | 8
Chassis | Jig | Manufacture | Wood |  | 0% | 2023-09-09 | 2023-09-16 | 8
Electrical | Mounting | Manufacture | Megasquirt |  | 0% | 2023-09-09 | 2023-09-16 | 8
Electrical | Mounting | Manufacture | Microsquirt |  | 0% | 2023-09-09 | 2023-09-16 | 8
Aerodynamics | Nose | Design | Nose | Owen | 75% | 2023-09-09 | 2023-09-16 | 8
Drivetrain | Power Transfer | Design | Half Shaft | Joey | 0% | 2023-09-09 | 2023-09-16 | 8
Controls | Pedal Tray | Design | Mounting | Colin/Kensly | 0% | 2023-09-09 | 2023-09-16 | 8
Controls | Ergonomics | Design | Dash | Nathan | 0% | 2023-09-09 | 2023-09-16 | 8
Controls | Ergonomics | Design | Dash mount | Nathan | 0% | 2023-09-09 | 2023-09-16 | 8
Controls | Display | Design | Display | Nathan | 0% | 2023-09-09 | 2023-09-16 | 8
Electrical | Mounting | Design | sensors |  | 0% | 2023-09-09 | 2023-09-16 | 8
Business | Events | Business | LSU? (Least Priority) |  | 100% | 2023-09-09 | 2023-09-16 | 8
Powertrain | Exhaust | Design | Mounting | Jacob | 0% | 2023-09-16 | 2023-09-23 | 8
Chassis | Jig | Manufacture | 3d Print |  | 0% | 2023-09-16 | 2023-09-23 | 8
Chassis | Jig | Manufacture | Jig |  | 0% | 2023-09-16 | 2023-09-23 | 8
Aerodynamics | Nose | Design | Mounting | Owen | 0% | 2023-09-16 | 2023-09-23 | 8
Drivetrain | Brakes | Design | Resevoir and Mount | Hayden/Brennan | 0% | 2023-09-16 | 2023-09-23 | 8
Controls | Display | Design | Wiring | Nathan | 0% | 2023-09-16 | 2023-09-23 | 8
Controls | Display | Design | Programming | Nathan | 0% | 2023-09-16 | 2023-09-23 | 8
Drivetrain | Chassis Mounting | Design | Tabs | DJ | 0% | 2023-09-16 | 2023-09-23 | 8
Electrical | Mounting | Design | Battery |  | 100% | 2023-09-16 | 2023-09-23 | 8
Electrical | Mounting | Manufacture | sensors |  | 0% | 2023-09-16 | 2023-09-23 | 8
Business | PR | Business | September Newsletter |  | 0% | 2023-09-16 | 2023-09-23 | 8
Powertrain | Cooling | Manufacture | Radiators |  | 0% | 2023-09-23 | 2023-09-30 | 8
Powertrain | Engine | Design | Engine Mounting | Zach | 0% | 2023-09-23 | 2023-09-30 | 8
Aerodynamics | Diffuser | Design | Diffuser | Matthew + Thang | 50% | 2023-09-23 | 2023-09-30 | 8
Controls | Ergonomics | Design | Seatbelt Mount | Owen | 0% | 2023-09-23 | 2023-09-30 | 8
Electrical | Sensors | Design | Brake Light |  | 0% | 2023-09-23 | 2023-09-30 | 8
Electrical | Mounting | Manufacture | coil |  | 0% | 2023-09-23 | 2023-09-30 | 8
Electrical | Mounting | Manufacture | AFR |  | 0% | 2023-09-23 | 2023-09-30 | 8
Business | Events | Business | Alabama Tailgate |  | 0% | 2023-09-23 | 2023-09-30 | 8
Business | Merchandise | Business | T-shirts |  | 0% | 2023-09-23 | 2023-09-30 | 8
Business | Merchandise | Business | Polos |  | 0% | 2023-09-23 | 2023-09-30 | 8
Suspension | Bellcrank | Manufacture | Front Bellcrank |  | 0% | 2023-09-30 | 2023-10-07 | 8
Suspension | Bellcrank | Manufacture | Rear Bellcrank |  | 100% | 2023-09-30 | 2023-10-07 | 8
Powertrain | Fuel | Design | Fuel Tank | Will | 25% | 2023-09-30 | 2023-10-07 | 8
Controls | Floorplate | Manufacture | Mold |  | 0% | 2023-09-30 | 2023-10-07 | 8
Controls | Firewall | Manufacture | Mold |  | 0% | 2023-09-30 | 2023-10-07 | 8
Drivetrain | Chassis Mounting | Manufacture | Diff Plates |  | 0% | 2023-09-30 | 2023-10-07 | 8
Drivetrain | Power Transfer | Manufacture | Sprocket |  | 0% | 2023-09-30 | 2023-10-07 | 8
Drivetrain | Power Transfer | Manufacture | Sprocket Mount |  | 0% | 2023-09-30 | 2023-10-07 | 8
Aerodynamics | Front Wing | Design | Front Wing | Leon + Kelsie | 5% | 2023-09-30 | 2023-10-07 | 8
Electrical | Sensors | Design | Wheel Hub Sensors |  | 90% | 2023-09-30 | 2023-10-07 | 8
Electrical | Mounting | Manufacture | Battery |  | 0% | 2023-09-30 | 2023-10-07 | 8
Powertrain | Fuel | Design | Injector Mount | Jacob | 55% | 2023-10-07 | 2023-10-14 | 8
Controls | Floorplate | Manufacture | Floorplate |  | 0% | 2023-10-07 | 2023-10-14 | 8
Controls | Ergonomics | Manufacture | Dash |  | 0% | 2023-10-07 | 2023-10-14 | 8
Controls | Firewall | Manufacture | Firewall |  | 0% | 2023-10-07 | 2023-10-14 | 8
Controls | Shifting | Manufacture | Mechanical Shifting |  | 0% | 2023-10-07 | 2023-10-14 | 8
Aerodynamics | Molds | Design | Manufacture Technique | All | 50% | 2023-10-07 | 2023-10-14 | 8
Controls | Shifting | Design | Mechanical Shifting | Kensly | 0% | 2023-10-07 | 2023-10-14 | 8
Electrical | Sensors | Design | Powertrain/Body Sensors |  | 0% | 2023-10-07 | 2023-10-14 | 8
Suspension | Tabs | Design | Tabs | All | 0% | 2023-10-14 | 2023-10-21 | 8
Suspension | Rods | Manufacture | Steering |  | 0% | 2023-10-14 | 2023-10-21 | 8
Suspension | Rods | Manufacture | Toe |  | 0% | 2023-10-14 | 2023-10-21 | 8
Powertrain | Fuel | Design | Fuel Tank Mount | Will | 0% | 2023-10-14 | 2023-10-21 | 8
Aerodynamics | Sidepod | Design | Sidepod | Wehinmi | 26% | 2023-10-14 | 2023-10-21 | 8
Controls | Headrest | Design | Mold | Owen | 0% | 2023-10-14 | 2023-10-21 | 8
Controls | Headrest | Design | Headrest | Owen | 0% | 2023-10-14 | 2023-10-21 | 8
Controls | Headrest | Design | Mounting | Owen | 0% | 2023-10-14 | 2023-10-21 | 8
Drivetrain | Brakes | Manufacture | Front System |  | 0% | 2023-10-17 | 2023-10-24 | 8
Drivetrain | Brakes | Manufacture | Rear System |  | 0% | 2023-10-17 | 2023-10-24 | 8
Suspension | Control Arm | Manufacture | Control Arm |  | 0% | 2023-10-21 | 2023-10-28 | 8
Suspension | Rods | Manufacture | Front Push |  | 0% | 2023-10-21 | 2023-10-28 | 8
Suspension | Rods | Manufacture | Rear Push |  | 0% | 2023-10-21 | 2023-10-28 | 8
Powertrain | Fuel | Design | Filter Mount | Jacob | 0% | 2023-10-21 | 2023-10-28 | 8
Powertrain | Fuel | Design | Regulator Mount | Jacob | 0% | 2023-10-21 | 2023-10-28 | 8
Powertrain | Fuel | Design | Pump Mount | Jacob | 0% | 2023-10-21 | 2023-10-28 | 8
Powertrain | Intake | Design | Mounting | Jacob | 0% | 2023-10-21 | 2023-10-28 | 8
Powertrain | Cooling | Design | Catch Can Mount | Mayo/Harvey | 0% | 2023-10-21 | 2023-10-28 | 8
Powertrain | Engine | Design | Catch Can Mount | Mayo/Harvey | 0% | 2023-10-21 | 2023-10-28 | 8
Controls | Firewall | Manufacture | Mounting |  | 0% | 2023-10-21 | 2023-10-28 | 8
Drivetrain | Chassis Mounting | Manufacture | Jig |  | 0% | 2023-10-21 | 2023-10-28 | 8
Aerodynamics | Rear Wing | Design | Rear Wing | Leon + Kelsie | 5% | 2023-10-21 | 2023-10-28 | 8
Electrical | Battery Box | Design | Battery Box |  | 0% | 2023-10-21 | 2023-10-28 | 8
Business | PR | Business | October Newsletter |  | 0% | 2023-10-21 | 2023-10-28 | 8
Suspension | Tabs | Manufacture | Tabs |  | 0% | 2023-10-28 | 2023-11-04 | 8
Powertrain | Fuel | Manufacture | Filler Neck |  | 0% | 2023-10-28 | 2023-11-04 | 8
Chassis | Chassis | Manufacture | Weld Tubes |  | 0% | 2023-10-28 | 2023-11-04 | 8
Chassis | Chassis | Manufacture | Chassis |  | 0% | 2023-10-28 | 2023-11-04 | 8
Controls | Pedal Tray | Manufacture | Mounting |  | 0% | 2023-10-28 | 2023-11-04 | 8
Powertrain | Engine | Manufacture | Engine Mounting |  | 0% | 2023-10-28 | 2023-11-04 | 8
Powertrain | Fuel | Manufacture | Filter Mount |  | 0% | 2023-10-28 | 2023-11-04 | 8
Powertrain | Fuel | Manufacture | Regulator Mount |  | 0% | 2023-10-28 | 2023-11-04 | 8
Powertrain | Fuel | Manufacture | Pump Mount |  | 0% | 2023-10-28 | 2023-11-04 | 8
Powertrain | Engine | Manufacture | Catch Can Mount |  | 0% | 2023-10-28 | 2023-11-04 | 8
Powertrain | Exhaust | Manufacture | Mounting |  | 0% | 2023-10-28 | 2023-11-04 | 8
Powertrain | Intake | Manufacture | Mounting |  | 0% | 2023-10-28 | 2023-11-04 | 8
Powertrain | Fuel | Manufacture | Fuel Tank Mount |  | 0% | 2023-10-28 | 2023-11-04 | 8
Powertrain | Cooling | Manufacture | Mounting |  | 0% | 2023-10-28 | 2023-11-04 | 8
Powertrain | Cooling | Manufacture | Catch Can Mount |  | 0% | 2023-10-28 | 2023-11-04 | 8
Chassis | Front | Manufacture | Anti Intrusion Plate |  | 0% | 2023-10-28 | 2023-11-04 | 8
Controls | Floorplate | Manufacture | Mounting |  | 0% | 2023-10-28 | 2023-11-04 | 8
Controls | Ergonomics | Manufacture | Dash mount |  | 0% | 2023-10-28 | 2023-11-04 | 8
Controls | Headrest | Manufacture | Mounting |  | 0% | 2023-10-28 | 2023-11-04 | 8
Drivetrain | Chassis Mounting | Manufacture | Tabs |  | 0% | 2023-10-28 | 2023-11-04 | 8
Drivetrain | Brakes | Manufacture | Resevoir and Mount |  | 0% | 2023-10-28 | 2023-11-04 | 8
Controls | Ergonomics | Manufacture | Seatbelt Mount |  | 0% | 2023-10-28 | 2023-11-04 | 8
Aerodynamics | Diffuser | Design | Mounting | Matthew + Thang | 10% | 2023-10-28 | 2023-11-04 | 8
Aerodynamics | Front Wing | Design | Mounting | Leon + Kelsie | 0% | 2023-10-28 | 2023-11-04 | 8
Aerodynamics | Rear Wing | Design | Mounting | Leon + Kelsie | 0% | 2023-10-28 | 2023-11-04 | 8
Aerodynamics | Sidepod | Design | Mounting | Wehinmi | 0% | 2023-10-28 | 2023-11-04 | 8
Controls | Seat | Design | Mounting | Kenslie | 0% | 2023-10-28 | 2023-11-04 | 8
Controls | Display | Design | Mounting | Nathan | 0% | 2023-10-28 | 2023-11-04 | 8
Business | Events | Business | Kentucky Tailgate |  | 0% | 2023-10-28 | 2023-11-04 | 8
Suspension | Wheel attach | Manufacture | Wheel Lugs |  | 0% | 2023-11-04 | 2023-11-11 | 8
Aerodynamics | Molds | Manufacture | Molds | All | 0% | 2023-11-04 | 2023-11-11 | 8
Powertrain | Fuel | Design | System | Will | 0% | 2023-11-04 | 2023-11-11 | 8
Drivetrain | Chassis Mounting | Manufacture | Tensioner |  | 0% | 2023-11-04 | 2023-11-11 | 8
Suspension | Upright | Manufacture | Front Upright |  | 0% | 2023-11-11 | 2023-11-18 | 8
Suspension | Upright | Manufacture | Rear Upright |  | 0% | 2023-11-11 | 2023-11-18 | 8
Aerodynamics | Top Plate | Manufacture | Top Plate |  | 0% | 2023-11-11 | 2023-11-18 | 8
Aerodynamics | Bodywork | Manufacture | Bodywork |  | 0% | 2023-11-11 | 2023-11-18 | 8
Powertrain | Intake | Design | Ram Air Intake | Austin | 0% | 2023-11-11 | 2023-11-18 | 8
Controls | Steering | Manufacture | Column Mount |  | 0% | 2023-11-11 | 2023-11-18 | 8
Controls | Steering | Manufacture | Column |  | 0% | 2023-11-11 | 2023-11-18 | 8
Controls | Steering | Manufacture | Rack Mount |  | 0% | 2023-11-11 | 2023-11-18 | 8
Controls | Seat | Manufacture | Mounting |  | 0% | 2023-11-11 | 2023-11-18 | 8
Business | Sponsorships | Business | Fall Sponsorship Reachout Cutoff |  | 0% | 2023-11-11 | 2023-11-18 | 8
Suspension | Upright | Manufacture | Camber Adjustment |  | 0% | 2023-11-18 | 2023-11-25 | 8
Suspension | Wheel attach | Manufacture | Wheel nuts |  | 80% | 2023-11-18 | 2023-11-25 | 8
Aerodynamics | Bodywork | Manufacture | Mounting |  | 0% | 2023-11-18 | 2023-11-25 | 8
Powertrain | Fuel | Manufacture | Fuel Tank |  | 0% | 2023-11-18 | 2023-11-25 | 8
Powertrain | Cooling | Design | Catch Can | Mayo/Harvey | 0% | 2023-11-18 | 2023-11-25 | 8
Powertrain | Engine | Design | Catch Can | Mayo/Harvey | 0% | 2023-11-18 | 2023-11-25 | 8
Drivetrain | Brakes | Manufacture | Buttons |  | 0% | 2023-11-18 | 2023-11-25 | 8
Electrical | Battery Box | Manufacture | Battery Box |  | 0% | 2023-11-18 | 2023-11-25 | 8
Business | PR | Business | November Newsletter |  | 0% | 2023-11-18 | 2023-11-25 | 8
Chassis | Chassis | Manufacture | Send out for Powder Coat |  | 0% | 2023-11-23 | 2023-11-30 | 8
Suspension | Spindle | Manufacture | Front spindle |  | 0% | 2023-11-25 | 2023-12-02 | 8
Suspension | Spindle | Manufacture | Rear Spindle |  | 0% | 2023-11-25 | 2023-12-02 | 8
Powertrain | Exhaust | Manufacture | 1/4 Wave Resonator |  | 0% | 2023-12-09 | 2023-12-16 | 8
Controls | Display | Manufacture | Display |  | 0% | 2023-12-09 | 2023-12-16 | 8
Controls | Display | Manufacture | Wiring |  | 0% | 2023-12-09 | 2023-12-16 | 8
Controls | Display | Manufacture | Mounting |  | 0% | 2023-12-09 | 2023-12-16 | 8
Powertrain | Exhaust | Manufacture | Helmholtz Resonator |  | 0% | 2023-12-09 | 2023-12-16 | 8
Powertrain | Intake | Manufacture | Runner |  | 0% | 2023-12-09 | 2023-12-16 | 8
Powertrain | Cooling | Manufacture | Aluminium Tubing |  | 0% | 2023-12-09 | 2023-12-16 | 8
Powertrain | Cooling | Manufacture | Hoses |  | 0% | 2023-12-09 | 2023-12-16 | 8
Drivetrain | Power Transfer | Manufacture | Half Shaft |  | 0% | 2023-12-09 | 2023-12-16 | 8
Suspension | Anti Roll bar | Manufacture | Anti Roll bar |  | 0% | 2023-12-09 | 2023-12-16 | 8
Business | PR | Business | December Newsletter |  | 0% | 2023-12-16 | 2023-12-23 | 8
Powertrain | Intake | Design | Plenum | Jacob | 0% | 2023-12-23 | 2023-12-30 | 8
Powertrain | Intake | Design | Restrictor | Jacob | 0% | 2023-12-23 | 2023-12-30 | 8
Business | Competition | Business | Book Hotels |  | 0% | 2023-12-24 | 2023-12-31 | 8
Business | Competition | Business | Book Transportation |  | 0% | 2023-12-24 | 2023-12-31 | 8
Business | Competition | Business | Ask for CAVS Trailer |  | 100% | 2023-12-25 | 2024-01-01 | 8
Controls | Display | Manufacture | Programming |  | 0% | 2023-12-30 | 2024-01-06 | 8
Powertrain | Exhaust | Manufacture | Muffler |  | 0% | 2023-12-30 | 2024-01-06 | 8
Aerodynamics | Nose | Manufacture | Nose |  | 0% | 2024-01-06 | 2024-01-13 | 8
Drivetrain | Power Transfer | Manufacture | Boots |  | 0% | 2024-01-06 | 2024-01-13 | 8
Controls | Shifting | Manufacture | Motor Mount |  | 0% | 2024-01-06 | 2024-01-13 | 8
Controls | Pedal Tray | Manufacture | Pedal Tray |  | 0% | 2024-01-06 | 2024-01-13 | 8
Powertrain | Exhaust | Manufacture | Tubing |  | 0% | 2024-01-06 | 2024-01-13 | 8
Controls | Clutch | Manufacture | Clutch |  | 0% | 2024-01-06 | 2024-01-13 | 8
Aerodynamics | Top Plate | Manufacture | Mounting |  | 0% | 2024-01-13 | 2024-01-20 | 8
Aerodynamics | Rear Wing | Manufacture | Mounting |  | 0% | 2024-01-13 | 2024-01-20 | 8
Aerodynamics | Front Wing | Manufacture | Mounting |  | 0% | 2024-01-13 | 2024-01-20 | 8
Aerodynamics | Nose | Manufacture | Mounting |  | 0% | 2024-01-13 | 2024-01-20 | 8
Aerodynamics | Sidepod | Manufacture | Mounting |  | 0% | 2024-01-13 | 2024-01-20 | 8
Controls | Shifting | Manufacture | Wiring |  | 0% | 2024-01-13 | 2024-01-20 | 8
Controls | Shifting | Manufacture | Controller Mounting |  | 0% | 2024-01-13 | 2024-01-20 | 8
Controls | Headrest | Manufacture | Mold |  | 0% | 2024-01-13 | 2024-01-20 | 8
Business | PR | Business | January Newsletter |  | 0% | 2024-01-16 | 2024-01-23 | 8
Aerodynamics | Sidepod | Manufacture | Sidepod |  | 0% | 2024-01-20 | 2024-01-27 | 8
Powertrain | Fuel | Manufacture | Injector Mount |  | 0% | 2024-01-20 | 2024-01-27 | 8
Powertrain | Cooling | Manufacture | Cooling Fill Cap |  | 0% | 2024-01-20 | 2024-01-27 | 8
Controls | Shifting | Manufacture | Paddles |  | 0% | 2024-01-20 | 2024-01-27 | 8
Controls | Steering | Manufacture | Wheel |  | 0% | 2024-01-20 | 2024-01-27 | 8
Controls | Headrest | Manufacture | Headrest |  | 0% | 2024-01-20 | 2024-01-27 | 8
Electrical | Harness | Manufacture | Harness |  | 0% | 2024-01-20 | 2024-01-27 | 8
Business | Merchandise | Business | Team Jackets |  | 0% | 2024-01-20 | 2024-01-27 | 8
Aerodynamics | Front Wing | Manufacture | Front Wing |  | 0% | 2024-01-27 | 2024-02-03 | 8
Powertrain | Engine | Manufacture | Catch Can |  | 0% | 2024-01-27 | 2024-02-03 | 8
Controls | Shifting | Manufacture | Code |  | 0% | 2024-01-27 | 2024-02-03 | 8
Powertrain | Cooling | Manufacture | Catch Can |  | 0% | 2024-01-27 | 2024-02-03 | 8
Aerodynamics | Rear Wing | Manufacture | Rear Wing |  | 0% | 2024-02-03 | 2024-02-10 | 8
Powertrain | Intake | Manufacture | Plenum |  | 0% | 2024-02-03 | 2024-02-10 | 8
Powertrain | Intake | Manufacture | Restrictor |  | 0% | 2024-02-03 | 2024-02-10 | 8
Powertrain | Fuel | Manufacture | System |  | 0% | 2024-02-03 | 2024-02-10 | 8
Electrical | Sensors | Manufacture | Install Sensors |  | 0% | 2024-02-03 | 2024-02-10 | 8
Drivetrain | Brakes | Manufacture | Bleed |  | 0% | 2024-02-10 | 2024-02-17 | 8
Powertrain | Intake | Manufacture | Ram Air Intake |  | 0% | 2024-02-10 | 2024-02-17 | 8
Controls | Clutch | Manufacture | Bleed |  | 0% | 2024-02-10 | 2024-02-17 | 8
Aerodynamics | Diffuser | Manufacture | Diffuser |  | 0% | 2024-02-17 | 2024-02-24 | 8
Chassis | Pushbar | Design | Pushbar |  | 0% | 2024-02-17 | 2024-02-24 | 8
Business | PR | Business | Febuary Newsletter |  | 0% | 2024-02-17 | 2024-02-24 | 8
Aerodynamics | Diffuser | Manufacture | Mounting |  | 0% | 2024-02-21 | 2024-02-28 | 8
Chassis | Pushbar | Manufacture | Pushbar |  | 0% | 2024-03-01 | 2024-03-08 | 8
Business | Sponsorships | Business | Spring Sponsorship Reachout Cutoff |  | 0% | 2024-03-09 | 2024-03-16 | 8
Business | PR | Business | March Newsletter |  | 0% | 2024-03-16 | 2024-03-23 | 8
Chassis | Front | Manufacture | Impact Attenuator |  | 0% | 2024-03-23 | 2024-03-30 | 8
Business | Competition | Business | Business Case |  | 0% | 2024-03-30 | 2024-04-06 | 8
Business | PR | Business | April Newsletter |  | 0% | 2024-04-20 | 2024-04-27 | 8
Business | Events | Business | Showcase Day |  | 0% | 2024-04-21 | 2024-04-28 | 8
Business | Competition | Business | Cost Presentation |  | 0% | 2024-04-24 | 2024-05-01 | 8
Business | PR | Business | May Newsletter |  | 0% | 2024-05-18 | 2024-05-25 | 8
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
| Competition |  |  |  | 0% | -7
Business | Competition | Business | Talk about finals |  |  | 2024-01-16 | 2024-01-16
| Competition |  |  |  | 0% | -7
Insert new rows ABOVE this one

## Design Reports
|  |  |  | Project Start: |  | 2022-07-01
|  |  |  | Display Week: |  | 7 |  |  | 2022-08-08 | [6 empty] | 2022-08-15 | [6 empty] | 2022-08-22 | [6 empty] | 2022-08-29 | [6 empty] | 2022-09-05 | [6 empty] | 2022-09-12 | [6 empty] | 2022-09-19 | [6 empty] | 2022-09-26 | [6 empty] | 2022-10-03 | [6 empty] | 2022-10-10 | [6 empty] | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05 | [6 empty] | 2022-12-12 | [6 empty] | 2022-12-19 | [6 empty] | 2022-12-26 | [6 empty] | 2023-01-02 | [6 empty] | 2023-01-09 | [6 empty] | 2023-01-16 | [6 empty] | 2023-01-23 | [6 empty] | 2023-01-30 | [6 empty] | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27
 | time axis 2022-08-08 to 2023-03-05
Section | System | Phase | Part | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2022-08-08 to 2023-03-05
|  | Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule. |  |  |  | -7
Aerodynamics |  |  | Front Wing w/ mounting |  | 0% | 2023-10-07 | 2023-10-14 | 8
Aerodynamics |  |  | Rear Wing w/ mounting |  | 0% | 2023-10-28 | 2023-11-04 | 8
Aerodynamics | sidepanels, toplate and nose |  | Bodywork w/ mounting |  | 0% | 2023-10-21 | 2023-10-28 | 8
Aerodynamics |  |  | Sidepod w/ mounting |  | 0% | 2023-10-21 | 2023-10-28 | 8
Aerodynamics |  |  | Diffuser w/ mounting |  | 0% | 2023-09-30 | 2023-10-07 | 8
Aerodynamics |  |  | Full Car aerodynamic analysis |  | 0% | 2023-12-24 | 2023-12-31 | 8
Aerodynamics |  |  | Cost Report |  | 0% |  | 1900-01-06
Aerodynamics |  |  | Spec sheet |  | 0% |  | 1900-01-06
Business |  |  | Business Case |  | 0% |  | 1900-01-06
Business | Actually due on 3rd |  | Cost Report |  | 0% |  | 1900-01-06
Chassis | how to create, how to analyze |  | Chassis |  | 5% | 2023-10-01 | 2023-10-08 | 8
Chassis |  |  | jig |  | 0% | 2023-10-01 | 2023-10-08 | 8
Chassis |  |  | Cost Report |  | 0% |  | 1900-01-06
Chassis |  |  | Spec sheet |  | 0% |  | 1900-01-06
Controls |  |  | Pedal Tray |  | 0% | 2023-09-09 | 2023-09-16 | 8
Controls |  |  | Steering assembly |  | 0% | 2023-08-26 | 2023-09-02 | 8
Controls | physical and code |  | Shifting assembly |  | 0% | 2023-09-02 | 2023-09-09 | 8
Controls |  |  | Display |  | 0% | 2023-09-16 | 2023-09-23 | 8
Controls | seat, headrest, position, steering wheel |  | Ergonomics |  | 0% | 2023-11-04 | 2023-11-11 | 8
Controls |  |  | Cost Report |  | 0% |  | 1900-01-06
Controls |  |  | Spec sheet |  | 0% |  | 1900-01-06
Drivetrain |  |  | Sprocket |  | 0% | 2023-08-12 | 2023-08-19 | 8
Drivetrain | mounting, tensioning |  | Dif |  | 0% | 2023-09-02 | 2023-09-09 | 8
Drivetrain | Geometry, force analysis |  | Brakes |  | 0% | 2023-09-23 | 2023-09-30 | 8
Drivetrain | Cooling analysis |  | Rotors |  | 0% | 2023-09-23 | 2023-09-30 | 8
Drivetrain |  |  | Cost Report |  | 0% |  | 1900-01-06
Drivetrain |  |  | Spec sheet |  | 0% |  | 1900-01-06
Electrical | how to create, how to analyze, data aq |  | Electrical |  | 0% | 2024-02-10 | 2024-02-17 | 8
Electrical |  |  | Cost Report |  | 0% |  | 1900-01-06
Electrical |  |  | Spec sheet |  | 0% |  | 1900-01-06
Powertrain |  |  | Cost Report |  | 0% |  | 1900-01-06
Powertrain |  |  | Exhaust |  | 0% | 2023-09-23 | 2023-09-30 | 8
Powertrain |  |  | Intake |  | 0% | 2023-09-16 | 2023-09-23 | 8
Powertrain |  |  | Cooling |  | 0% | 2023-09-16 | 2023-09-23 | 8
Powertrain |  |  | Tuning |  | 0% | 2023-12-24 | 2023-12-31 | 8
Powertrain |  |  | Spec sheet |  | 0% |  | 1900-01-06
Suspension |  |  | Cost Report |  | 0% |  | 1900-01-06
Suspension |  |  | Spindle |  | 0% | 2023-06-24 | 2023-07-01 | 8
Suspension |  |  | Uprights |  | 0% | 2023-06-24 | 2023-07-01 | 8
Suspension |  |  | Kinematics |  | 0% | 2023-08-05 | 2023-08-12 | 8
Suspension |  |  | Spec sheet |  | 0% |  | 1900-01-06
Insert new rows ABOVE this one

## Weekly Schedule
| Presentation |  |  | Cleaning: Section Lead |  | Member |  | Member
Saturday | Name | Email | SATURDAY | Name | Email | Name | Email | Name | Email
2023-08-19
2023-08-26
2023-09-02
2023-09-09
2023-09-16
2023-09-23
2023-09-30
2023-10-07
2023-10-14
2023-10-21
2023-10-28
2023-11-04
2023-11-11
2023-11-18
2023-11-25
2023-12-02
2023-12-09
2023-12-16
2023-12-23
2023-12-30
2024-01-06
2024-01-13
2024-01-20
2024-01-27
2024-02-03
2024-02-10
2024-02-17
2024-02-24
2024-03-02
2024-03-09
2024-03-16
2024-03-23
2024-03-30
2024-04-06
2024-04-13
2024-04-20
2024-04-27
2024-05-04